## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Help | Erinnert den Benutzer der App an die Einnahme von Medikamenten, welche vom Arzt in die Liste der einzunehmenden Medikamente eingefügt wurde. Die Medikamente werden mit der empfohlenen Dosis eingetragen und dem Patienten für die Einnahme mit Anzeige der empfohlenen Dosis angezeigt. | high | 80h |  |  | work in prorgress
2 | Medication Alert | Ein Reminder erinnert Patient an Medikamenteinnahme zur richtigen Zeit und in der korrekten Dosis | medium | 80h |  |  | waiting
3 | Skills | Der Patient kann seine definierten Skills -Funktion aufrufen | low | 40h |  |  | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Mainview | Create the Mainview of the Application in which the different views are displayed and a ViewManager | Main Window | vandj2 | high | 10 |  |  | work in progress
1.2 | 1 | Helpview | Create the Helpview with its Controller and also beginn with the corresponding | UI, Presneter | medim1 | high | 8 |  |  | work in progress
1.3 | 1 | Help Settings View | Settings view | UI, Presenter | messv1 | high | 8 |  |  | work in progress
1.4 | 1 | Mockup Data | Create Mockup data in the Model and the corresponding Entities (ContactPerson) | Model, DataAccess | dagde1 | high | 4 |  |  | work in progress
1.5 | 1 | LoginView | Create a Login view for later user specific Data Handling | UI, Presenter | gnagj1 | low | 6 |  |  | done
1.6 | 1 | LoginManager | Based on the Login Data given the Manager must grant access or dissalow by checking data from database | BLL | vonkc2 | low | 19 |  |  | work in progress
1.7
1.8
1.9 | 1 | User Data Manager | Create a Manager that gets the right Data based on the View and the logged in user | BLL | vandj2 | medium | 19 |  |  | waiting
2.1 | 2 | MainView Settings |  | UI | vandj2 |  | 10 |  |  | work in progress
3.1 | 2 | HelpView |  | UI | medim1 |  | 10 |  |  | work in progress
2.3 | 2 | LoginManager | LoginManager with Interface für DataAccess und DatenBank-Klasse | BLL | vonkc2 |  | 10 |  |  | work in progress
2.4 | 2 | MedicationView Settings |  | UI | dagde1 |  | 10 |  |  | work in progress
2.5 | 2 | Medication View | View für Meeication und Reminder | UI, BLL | gnagj1 |  | 8 |  |  | work in progress
2.6 | 2 | Help Settings View | Settings view | UI, Presenter | messv1 | high | 8
2
2
2
4.1 | 3 | Data Model | Design the Data Model for the Persistent Storage | Database |  | high | 12 |  |  | waiting
4.2 | 3 | Data Access | Create the Database Access Component, implementing the DataAccess Interface | DataAccess |  | high | 18 |  |  | waiting
4.3 | 3 | Testing | Test the current Application on Errors | All |  | high | 10 |  |  | waiting