## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Settings | Setting up different Configurations for the other Modules | high | 100h
2 | Medication Alert | Ein Reminder erinnert Patient an Medikamenteinnahme zur richtigen Zeit und in der korrekten Dosis | medium | 200h
3 | Skills | Der Patient kann seine definierten Skills -Funktion aufrufen | low | 400h
4 | Help | Erinnert den Benutzer der App an die Einnahme von Medikamenten, welche vom Arzt in die Liste der einzunehmenden Medikamente eingefügt wurde. Die Medikamente werden mit der empfohlenen Dosis eingetragen und dem Patienten für die Einnahme mit Anzeige der empfohlenen Dosis angezeigt. | high | 100h

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | high | 8 | 6 | 5 | work in progress