## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Help | Erinnert den Benutzer der App an die Einnahme von Medikamenten, welche vom Arzt in die Liste der einzunehmenden Medikamente eingefügt wurde. Die Medikamente werden mit der empfohlenen Dosis eingetragen und dem Patienten für die Einnahme mit Anzeige der empfohlenen Dosis angezeigt. | high | 80h |  |  | work in prorgress
2 | Medication Alert | Ein Reminder erinnert Patient an Medikamenteinnahme zur richtigen Zeit und in der korrekten Dosis | medium | 80h |  |  | waiting
3 | Skills | Der Patient kann seine definierten Skills -Funktion aufrufen | low | 40h |  |  | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status | Running Total Effort Org. | Running Total Effort Upd. | Running Total Effort Act.
1.1 | 1 | Mainview | Create the Mainview of the Application in which the different views are displayed and a ViewManager | Main Window | vandj2 | high | 10 |  |  | waiting | 10 | 0 | 0
1.2 | 1 | Helpview | Create the Helpview with its Controller and also beginn with the corresponding | UI, Presneter | medim1 | high | 8 |  |  | waiting | 18 | 0 | 0
1.3 | 1 | Help Settings View | Settings view | UI, Presenter
1.4 | 1 | Mockup Data | Create Mockup data in the Model and the corresponding Entities (ContactPerson) | Model
1.5 | 1 | LoginView | Create a Login view for later user specific Data Handling | UI, Controller | gnagj1 | low | 6 |  |  | waiting | 28 | 0 | 0
1.6 | 1 | Model | Create a Model based on the Requirements for the Help Scenario | BLL | dagde1 | medium | 4 |  |  | waiting | 28 | 0 | 0
1.7 | 1 | LoginManager | Based on the Login Data given the Manager must grant access or dissalow by checking data from database | BLL | vonkc2 | low | 19 |  |  | waiting | 47 | 0 | 0
1.8 | 1 | User Data Manager | Create a Manager that gets the right Data based on the View and the logged in user | BLL | vandj2 | medium | 19 |  |  | waiting | 66 | 0 | 0
1.9
2.1 | 2 | MedicView | Create the MedicView with its Presenter and also beginn with the corresponding Settings view | UI, Persenter |  | medium | 16 |  |  | waiting | 16 | 0 | 0
3.1 | 2 | SkillsView | Create the SkillsView with its Presenter and also beginn with the corresponding Settings view | UI, Persenter |  | low | 8 |  |  | waiting | 24 | 0 | 0
2.3 | 2 | Testing | Test the current Application on Errors | All |  | high | 6 |  |  | waiting | 30 | 0 | 0
2.4 | 2 | Reminder | Reminder for due times to take medication, for each user and selected medic a timer needs to be created | ReminderComponent, Calendar |  | medium | 20 |  |  | waiting | 50 | 0 | 0
2.5 | 2 | Reminder | Solution to Push Reminder to User when not logged in. | RemeinderComponent |  | medium | 20 |  |  | waiting | 70 | 0 | 0
2.6 | 2 | Model | Edit the Model to store the medication data | Model |  | medium | 10 |  |  | waiting | 80 | 0 | 0
4.1 | 3 | Data Model | Design the Data Model for the Persistent Storage | Database |  | high | 12 |  |  | waiting | 12 | 0 | 0
4.2 | 3 | Data Access | Create the Database Access Component, implementing the DataAccess Interface | DataAccess |  | high | 18 |  |  | waiting | 30 | 0 | 0
4.3 | 3 | Testing | Test the current Application on Errors | All |  | high | 10 |  |  | waiting | 40 | 0 | 0