## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Help | Erinnert den Benutzer der App an die Einnahme von Medikamenten, welche vom Arzt in die Liste der einzunehmenden Medikamente eingefügt wurde. Die Medikamente werden mit der empfohlenen Dosis eingetragen und dem Patienten für die Einnahme mit Anzeige der empfohlenen Dosis angezeigt. | high | 80h |  |  | work in prorgress
2 | Medication Alert | Ein Reminder erinnert Patient an Medikamenteinnahme zur richtigen Zeit und in der korrekten Dosis | medium | 80h |  |  | waiting
3 | Skills | Der Patient kann seine definierten Skills -Funktion aufrufen | low | 40h |  |  | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Mainview | Create the Mainview of the Application in which the different views are displayed and a ViewManager | Main Window | vandj2 | high | 10 |  | 4 | done
1.2 | 1 | Helpview | Create the Helpview with its Controller and also beginn with the corresponding | UI, Presneter | medim1 | high | 8 | 8 |  | work in progress
1.3 | 1 | Help Settings View | Settings view | UI, Presenter | messv1 | high | 8 | 10 |  | work in progress
1.4 | 1 | Mockup Data | Create Mockup data in the Model and the corresponding Entities (ContactPerson) | Model, DataAccess | dagde1 | high | 4 | 2 | 2 | done
1.5 | 1 | LoginView | Create a Login view for later user specific Data Handling | UI, Presenter | gnagj1 | low | 6 | 2 | 2 | done
1.6 | 1 | LoginManager | Based on the Login Data given the Manager must grant access or dissalow by checking data from database | BLL | vonkc2 | low | 19 | 10 | 6 | done
2.1 | 2 | MainView Settings |  | UI | vandj2 | high | 10 |  | 10 | done
3.1 | 2 | HelpView |  | UI | medim1 | high | 10 |  |  | work in progress
2.3 | 2 | LoginManager | LoginManager with Interface für DataAccess und DatenBank-Klasse | BLL | vonkc2 | high | 10 | 6 | 6 | done
2.4 | 2 | Medication Settings View |  | UI | dagde1 | high | 10 | 12 |  | work in progress
2.5 | 2 | Medication View | View für Meeication und Reminder | UI, BLL | gnagj1 | high | 8 | 10 | 10 | done
2.6 | 2 | Help Settings View | Settings view | UI, Presenter | messv1 | high | 8 |  |  | work in progress
1.4 | 2 | Mockup Data | Create Mockup data in the Model and the corresponding Entities (ContactPerson) | Model, DataAccess | dagde1 | high | 4 | 2 | 2 | done
2.3 | 2 | Authentication | Encryption of passwords | BLL, LoginManager | vonkc2 | medium | 10 | 6 | 6 | done
2.7 | 2 | State | Find a Part that is likely to change to implement State Pattern | UI, BLL | gnagj1 |  | 6 |  | 4 | done
2.8 | 2 | Custom Data | Implement logic to get specific Data for the logged in User | User Data Manager, DataAccess | gnagj1 | medium | 10 |  | 4 | done
4.1 | 3 | Testing | Test the current Application on Errors | All | gnagj1 | high | 10 |  |  | work in progress
4.2 | 3 | Styling |  | UI | vandj2 | medium | 8 |  |  | work in progress
4.3 | 3 | Pseudo Persistent Storage | Allow acutal Data be viewed by Patient and Staff | DataAccess | vonkc2 | low | 8 |  |  | work in progress
3.1 | 3 | HelpView |  | UI | medim1 | high | 10 |  |  | work in progress
2.4 | 3 | Medication Settings View |  | UI | dagde1 | high | 10 | 12 |  | work in progress
2.6 | 3 | Help Settings View | Settings view | UI, Presenter | messv1 | high | 8 |  |  | work in progress