## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Help | Erinnert den Benutzer der App an die Einnahme von Medikamenten, welche vom Arzt in die Liste der einzunehmenden Medikamente eingefügt wurde. Die Medikamente werden mit der empfohlenen Dosis eingetragen und dem Patienten für die Einnahme mit Anzeige der empfohlenen Dosis angezeigt. | high | 70h
2 | Medication Alert | Ein Reminder erinnert Patient an Medikamenteinnahme zur richtigen Zeit und in der korrekten Dosis | medium | 150h
3 | Skills | Der Patient kann seine definierten Skills -Funktion aufrufen | low | 70h
4 | Persistent Storage | Store for the different Personal Data | high | 80h

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | System Architecture | design a software architecture taking into account ▶ system requirements ▶ incl. the need for persistent data storage ▶ architectural design patterns ▶ the Vaadin framework | All | gnagj1 | high | 1 |  |  | work in progress
1.2 | 1 | Package Diagram | Creating a UML package diagram to show the high-level structure of application. | All | vonkc2 | high | 1 |  |  | work in progress
1.3 | 1 | Class Diagramm | Create a Class Diagram / Domain Diagram for classes required | All |  | high | 2 |  |  | waiting
1.4 | 1 | Mainview | Create the Mainview of the Application in which the different views are displayed and a ViewManager | Main Window |  | high | 10 |  |  | waiting
1.5 | 1 | Helpview | Create the Helpview with its Controller and also beginn with the corresponding Settings view | UI, Controller |  | high | 8 |  |  | waiting
1.6 | 1 | Model | Create a Model based on the Requirements for the Help Scenario | BLL |  | medium | 4 |  |  | waiting
1.7 | 1 | LoginView | Create a Login view for later user specific Data Handling | UI, Controller |  | low | 6 |  |  | waiting
1.8 | 1 | User Data Manager | Create a Manager that gets the right Data based on the View and the logged in user | BLL |  | medium | 19 |  |  | waiting
1.9 | 1 | LoginManager | Based on the Login Data given the Manager must grant access or dissalow by checking data from database | BLL |  | low | 19 |  |  | waiting
2.1 | 2 | MedicView | Create the MedicView with its Controller and also beginn with the corresponding Settings view |  |  | high
3.1 | 2 | SkillsView | Create the SkillsView with its Controller and also beginn with the corresponding Settings view |  |  | low
2.3 | 2
2.4 | 2
2.5 | 2
2.6 | 2
2.7 | 2
2.8 | 2
2.9 | 2